## Slide 1
TCS
TATA
ATLAS
AI Tool for Learning And Search
RAG-Powered Internal Knowledge Assistant
Empowering knowledge discovery through intelligent algorithms
Prepared: May 2026 | Team: 2 Developers | Classification: Internal | Comcast × TCS

## Slide 2
Executive Summary
ATLAS — AI Tool for Learning And Search | Comcast × TCS | Confidential
~18,200
Lines of Code
2
Developers
8 Weeks
~2 Calendar Months
80
Total Person-Days
ATLAS is a RAG (Retrieval-Augmented Generation) application with a Python/FastAPI backend, React/TypeScript frontend, and containerized infrastructure (Podman Compose). Two developers working in parallel — one backend-focused, one frontend-focused — can deliver the full application in 8 weeks (2 calendar months).
Approach
Developer A (Backend) — builds the RAG pipeline, APIs, and integrations. Developer B (Frontend + DevOps) — builds the chat UI, Podman infrastructure, and testing. Both use AI coding assistants (GitHub Copilot) — reducing boilerplate and test effort by ~25%.

## Slide 3
Team Composition
ATLAS — AI Tool for Learning And Search | Comcast × TCS | Confidential
DEV A — Backend Developer
Level:
Mid-Senior (3+ years)
Effort:
40 Days
Duration:
8 Weeks
Core Skills Required:
Python async / FastAPI
REST APIs + SQL
LLM/RAG concepts
Confluence API
Vector databases (Qdrant)
DEV B — Frontend + DevOps
Level:
Mid-Senior (3+ years)
Effort:
40 Days
Duration:
8 Weeks
Core Skills Required:
React + TypeScript
Podman Compose
CI/CD + GitHub Actions
Kubernetes basics
Testing (vitest, k6)
Total: 80 person-days = 2 developers × 40 working days = 8 weeks elapsed

## Slide 4
Sprint 1 — Weeks 1 & 2
ATLAS — AI Tool for Learning And Search | Comcast × TCS | Confidential
Week 1
DEV A — Backend
Project setup, FastAPI skeleton, pydantic-settings config
Confluence REST API client (pagination, auth)
HTML parser + sentence-aware text chunker
DEV B — Frontend + DevOps
React project setup (Vite + TypeScript)
Podman Compose: backend + qdrant + ollama + frontend
Basic chat UI layout (ChatContainer, ChatInput, MessageList)
Week 2
DEV A — Backend
Embedding service (Ollama nomic-embed-text)
Qdrant vector store (upsert, search, delete)
Ingestion endpoint (full refresh + incremental skip)
Health check endpoint
DEV B — Frontend + DevOps
MessageItem component (Markdown, code blocks, copy)
SSE client service (EventSource streaming)
useChat hook (useReducer + localStorage)
Container image for frontend (Node build → nginx)

## Slide 5
Sprint 2 — Weeks 3 & 4
ATLAS — AI Tool for Learning And Search | Comcast × TCS | Confidential
Week 3
DEV A — Backend
RAG service (retrieve → build context → prompt)
LLM abstraction (Ollama + Azure OpenAI + AMA Bespoke)
Chat endpoint with SSE streaming
Source citation injection in stream
DEV B — Frontend + DevOps
Source citations component (clickable links)
Conversation sidebar (list, search, rename, delete)
useFolders + useConversations hooks
Dark/light theme toggle (useTheme)
Week 4
DEV A — Backend
Conversation persistence (SQLite store)
Semantic cache (skip LLM for repeated queries)
Query rewriter (LLM rewrites vague questions)
Content + input guardrails
DEV B — Frontend + DevOps
File upload UI (drag & drop)
Mermaid diagram + image block rendering
Selection popup + query suggestions
Error boundary + responsive layout polish

## Slide 6
Sprint 3 — Weeks 5 & 6
ATLAS — AI Tool for Learning And Search | Comcast × TCS | Confidential
Week 5
DEV A — Backend
Authentication: JWT, user store, login/register API
API key auth + RBAC space access
Feedback collection endpoint
Re-ranker (cross-encoder LLM scoring)
DEV B — Frontend + DevOps
Login page + AuthContext
Feedback dashboard (admin view)
Frontend test suite (vitest: hooks + components)
run.ps1 / run.sh automation scripts
Week 6
DEV A — Backend
Jira integration (REST client + issue-to-chunks)
GitHub integration (file/PR ingestion)
Intent router (multi-source query routing)
File parser service (PDF, DOCX, CSV)
DEV B — Frontend + DevOps
TLS mode (cert generation, nginx HTTPS)
ELK stack profile (Elasticsearch + Kibana)
PostgreSQL profile + Alembic migrations
k6 load test scripts (smoke, load, stress)

## Slide 7
Sprint 4 — Weeks 7 & 8
ATLAS — AI Tool for Learning And Search | Comcast × TCS | Confidential
Week 7
DEV A — Backend
MCP server for VS Code Copilot (stdio proxy)
FlowIntel MCP client (SAT auth, tool discovery)
Slack bot + Teams bot integration
SSO/OIDC integration
DEV B — Frontend + DevOps
Kubernetes manifests (deployments, HPA, ingress)
CI/CD pipeline (GitHub Actions)
OpenTelemetry + Prometheus metrics setup
Corporate proxy CA cert injection
Week 8
DEV A — Backend
Backend test suite (pytest, unit + integration)
Entity extraction (Cognee-lite)
Bug fixes, edge cases, security hardening
API documentation (OpenAPI/Swagger)
DEV B — Frontend + DevOps
End-to-end testing + bug fixes
Documentation (README, .env.example, AGENTS.md)
Performance tuning + load testing
Final deployment verification

## Slide 8
Timeline View — 8-Week Delivery Plan
ATLAS — AI Tool for Learning And Search | Comcast × TCS | Confidential
Wk1
Wk2
Wk3
Wk4
Wk5
Wk6
Wk7
Wk8
Core RAG Pipeline
A
Chat UI & Frontend
B
LLM + Streaming
A
Auth + Enterprise
A
Infra & DevOps
B
Integrations & Bots
A
K8s + CI/CD
B
Testing & Polish
AB
Key Milestones
End of Week 2: Working prototype — ingest docs, ask questions, get AI answers (backend only)
End of Week 4: Full demo-ready app — chat UI + streaming + conversations + themes
End of Week 6: Enterprise features — auth, multi-source ingestion, caching, guardrails
End of Week 8: Production-ready — tested, load-tested, CI/CD, K8s, documented

## Slide 9
Effort Breakdown by Category
ATLAS — AI Tool for Learning And Search | Comcast × TCS | Confidential
Category | Days | Owner | Deliverables
Core RAG Pipeline | 10 | A | Confluence client, chunker, embeddings, vector store, RAG service, ingestion
LLM & Streaming | 8 | A | Multi-provider LLM, SSE streaming, prompt engineering, semantic cache, rewriter
Auth & Enterprise | 8 | A | JWT auth, SSO/OIDC, RBAC, guardrails, re-ranker, entity extraction
Integrations | 8 | A | Jira, GitHub, MCP server, FlowIntel, Slack/Teams bots, file parser
Backend Testing | 6 | A | Pytest suite (unit + integration), ~3,500 LOC test coverage
React Frontend | 16 | B | Chat UI, conversations, themes, file upload, Markdown/Mermaid, login
Podman & Infrastructure | 8 | B | Podman Compose (12 services), TLS, ELK, PostgreSQL profiles, scripts
CI/CD & Kubernetes | 6 | B | GitHub Actions pipeline, K8s manifests, HPA, ingress
Frontend Testing & QA | 6 | B | Vitest suite, k6 load tests, docs, final polish
Research & Learning | 4 | AB | RAG concepts, Qdrant, Ollama, LLM APIs (first 2 days each developer)
TOTAL | 80 | 2 | 40 days per developer × 2 developers = 8 weeks elapsed

## Slide 10
Effort Estimation Methodology
ATLAS — AI Tool for Learning And Search | Comcast × TCS | Confidential
1
Bottom-Up Estimation
47 feature tasks identified across all sprints
Each task estimated individually in hours
Tasks aggregated → 80 total person-days
Validated against team velocity benchmarks
2
Codebase Analysis
Actual codebase: ~18,200 lines of code measured
Industry standard: 50–100 LOC per developer/day
Without AI assistance: 182–364 dev-days needed
With GitHub Copilot (~25% boost): reduced to ~80 days ✅
3
Sprint Velocity
4 sprints × 2 weeks each = 8 weeks total
~10 story points per developer per sprint
80 total story points across full delivery
Aligns with mid-senior developer benchmarks
Estimation Confidence & Risk Factors
High Confidence ✅ — Core RAG + Frontend (already built & tested)
Medium ⚠️ — Infrastructure (corporate proxy/VPN variables)
Risk factors: +1 week VPN/proxy issues | +2–3 weeks if junior developers | +1 week major scope changes | Plan for 9 weeks for guaranteed delivery.

## Slide 11
Required Skills Matrix
ATLAS — AI Tool for Learning And Search | Comcast × TCS | Confidential
Skill | Priority | DEV A — Backend | DEV B — Frontend
Python 3.10+ (async) | MUST | Advanced — all backend code | Basic — scripts, debugging
FastAPI | MUST | Advanced — APIs, SSE, middleware | —
React + TypeScript | MUST | — | Advanced — all frontend code
Podman Compose | MUST | Basic — container image build | Advanced — 12-service compose
RAG / Vector DB / LLM | MUST | Intermediate — core architecture | Basic — understand the flow
REST API consumption | MUST | Advanced — Confluence, Jira, GitHub | Basic — SSE client
SQL (SQLite + PostgreSQL) | SHOULD | Intermediate — user/conversation store | —
Auth (JWT, OAuth2, OIDC) | SHOULD | Intermediate — backend auth | Basic — login UI
Kubernetes | SHOULD | — | Intermediate — manifests, HPA
CI/CD (GitHub Actions) | SHOULD | — | Intermediate — pipeline config

## Slide 12
Assumptions & Dependencies
ATLAS — AI Tool for Learning And Search | Comcast × TCS | Confidential
1
AI Coding Assistant Available
Both developers use GitHub Copilot — reduces boilerplate/test effort by ~25%
2
Confluence API Access Granted
API token and space access approved before Week 1 (otherwise use local test docs)
3
No Major Scope Changes
Feature set as defined; additional sources or UI features would extend timeline
4
Podman Available
Both developers have Podman installed (enterprise-approved, replaces Docker Desktop)
5
7–8 Productive Hours/Day
No context-switching to other projects during the 8-week sprint
6
Mid-Senior Developers
3+ years experience; if junior developers, add 2–3 weeks buffer to the plan
Risk Buffer
The 8-week plan has ~3 days of slack per developer built into Week 8. If corporate environment issues arise (proxy, VPN, access requests), this buffer absorbs 1 week of delays. For guaranteed delivery, plan for 9 weeks.

## Slide 13
Deliverables Summary
ATLAS — AI Tool for Learning And Search | Comcast × TCS | Confidential
Week 2
Working RAG Prototype
Ingest Confluence docs → ask questions → get AI answers
Backend pipeline proven end-to-end
Ready for internal engineering validation
Week 4
Demo-Ready Application
Full chat UI with streaming responses
Conversation history + dark/light mode
Ready for stakeholder demonstration
Week 6
Enterprise Features
Auth (JWT + RBAC), Jira/GitHub ingestion
Semantic caching, guardrails, file upload
Multi-source intent routing
Week 8
Production Package
CI/CD, K8s manifests, load tests complete
Slack/Teams bots, MCP server operational
Complete documentation, performance verified

## Slide 14
Production Cost Estimate — AWS EC2 + LLM (Enterprise Scale)
ATLAS — AI Tool for Learning And Search | Comcast × TCS | Confidential
Development Phase (One-Time)
Item | Duration | Cost Basis
Developer A (Backend) | 40 days | Per resource rate card (TCS)
Developer B (Frontend + DevOps) | 40 days | Per resource rate card (TCS)
Dev/Test Infrastructure | 8 weeks | $0 — Podman on developer laptops
Dev LLM costs (Ollama/AMA Bespoke) | 8 weeks | $0 — local Ollama or Comcast FlowContext (internal)
Production Monthly Infrastructure — AWS EC2/ECS/EKS
Component | Instance / Config | Monthly Cost | Notes
App Server (EC2/ECS) | t3.xlarge (4 vCPU, 16 GB) | ~$120 | FastAPI backend + nginx frontend
Qdrant Vector DB (EC2) | m5.large (2 vCPU, 8 GB) | ~$70 | Persistent EBS volume 50GB SSD
PostgreSQL (RDS) | db.t3.medium Multi-AZ | ~$80 | Conversations, feedback, users, graph links
Load Balancer (ALB) | Application Load Balancer | ~$20 | HTTPS termination + routing
Total AWS Infrastructure | Production-grade HA setup | ~$290/mo | Scales to 500+ concurrent users

## Slide 15
LLM Cost Analysis — FlowContext Models & Enterprise User Capacity
ATLAS — AI Tool for Learning And Search | Comcast × TCS | Confidential
FlowContext LLM Options (context.flow.cnap.comcast.net — Comcast Internal Gateway)
Model | Provider | Input/1M | Output/1M | Cost/Query | 200 Users/Mo | Recommendation
gpt-5-nano | Azure | $0.033 | $0.26 | ~$0.0002 | ~$0.60 | Ultra Cheap
gpt-5-mini | Azure | $0.163 | $1.30 | ~$0.001 | ~$3 | Best Value ⭐
claude-4-6-sonnet | AWS | $2.97 | $14.85 | ~$0.004 | ~$12 | Best Quality
nova-micro | AWS | $0.023 | $0.091 | ~$0.0003 | ~$0.90 | Alt Option
Total Production Monthly Cost by User Scale
User Scale | Queries/Day | AWS Infra | LLM (gpt-5-mini) | TOTAL/Month | Cost Per User
Small Team (50 users) | ~125 queries | ~$150 | ~$1 | ~$151/mo | ~$3.02/user
Medium Org (200 users) | ~500 queries | ~$290 | ~$3 | ~$293/mo | ~$1.47/user
Large Enterprise (500 users) | ~1,500 queries | ~$420 | ~$9 | ~$429/mo | ~$0.86/user
Enterprise (1,000+ users) | ~3,000+ queries | ~$650 | ~$18 | ~$668/mo | ~$0.67/user
All LLMs accessed via Comcast FlowContext — corporate approved, zero external data transfer. AWS costs estimated for us-east-1 region. Semantic cache reduces LLM calls by 30–60%.

## Slide 16
Recommended Developer Profiles
ATLAS — AI Tool for Learning And Search | Comcast × TCS | Confidential
DEV A — Backend Developer
Experience:
3–5 years Python development
MUST KNOW
FastAPI / Flask, async/await patterns
REST APIs, SQL, database design
LLM/ML experience with RAG systems
NICE TO HAVE
Confluence API, vector databases
RAG architecture and embedding models
OpenTelemetry + observability tooling
Title: Senior Python Developer / Backend Engineer
DEV B — Frontend + DevOps
Experience:
3–5 years React/TypeScript
MUST KNOW
React hooks, TypeScript, Vite build tooling
Podman Compose, container orchestration
CI/CD basics with GitHub Actions
NICE TO HAVE
Kubernetes, nginx, ELK stack
k6 load testing, vitest unit testing
OpenTelemetry + Prometheus metrics
Title: Senior Frontend Developer / Full-Stack Engineer

## Slide 17
TCS
TATA
Thank You!
ATLAS — AI Tool for Learning And Search
RAG-Powered Internal Knowledge Assistant | Comcast × TCS
523 Tests | 18,200 LOC | 8 Weeks | 2 Developers | ~$293/month for 200 users (AWS + FlowContext)